## Testing phase status
Testing phase status TechyBlocks Application
QA Issue Tracker & Engineering Status Log ¦ Techyblocks Platform Testing
Issue / Task ID | Trainer / Reporter Name | Reported Time | Module / Category | Reported Issue / Task Description | Associated File / Asset | Assigned Lead / Solver | Resolution / Action Taken | Resolved Status | Resolved Time | Remarks / Next Steps
ISS-001 | Vibha Prajapati | 2026-09-03 18:52 | Events & Interaction | Color change in letter 'T' sprite not triggering with block 'When this sprite is clicked' in multi-sprite action mode. | Screen Recording 2026-09-03 185243.mp4 | Diptiban Nayak | Recommended switching event trigger to 'When flag is clicked' using reference animation guide. | Resolved (Workaround) | 2026-09-04 08:35 | Logic confirmed operational by trainer; separate color rendering bug logged in ISS-007.
ISS-002 | Rudra Pratap Dubey | 2026-09-03 19:20 | Motion / Sensing | Sprite activity not working properly; sprite is not following mouse pointer. | Mouse Pointer Movement.mp4 | Diptiban Nayak | Verified pointer coordinates listener and block configuration. | Resolved | 2026-09-03 19:40 | Rudra confirmed mouse pointer tracking is working properly.
ISS-003 | Vibha Prajapati | 2026-09-03 20:15 | Animation Project | TECHYGUIDE animated project multi-sprite execution failing / needs validation. | project.techyguide | Diptiban Nayak | Provided sample project file 'Techyguide_Animation.techyguide' and walkthrough video 'Scratch_Techyguide_Animation.mp4'. | Resolved | 2026-09-04 08:35 | Trainer followed attached video and confirmed project issue solved.
ISS-004 | Rudra Pratap Dubey | 2026-09-04 08:14 | Assets & Sensing | 1. No Diver sprite available to catch fish project. 2. 'Touching other sprite' option not appearing in sensing dropdown. | Screenshot 2026-09-04 081419.png | Diptiban Nayak | Added Diver sprite to 'Choose a Sprite' modal and added complete Diver costumes to Techyblocks app. | Resolved | 2026-09-04 Update | Diver asset and costumes deployed; sensing dropdown option verified.
ISS-005 | Rudra Pratap Dubey | 2026-09-04 08:20 | Operators | Join operator missing from Operators palette; inquired about alternate blocks. | — | Diptiban Nayak | Investigated block availability and alternate string handling blocks. | Resolved | 2026-09-04 08:45 | Assisted trainer with operator configuration.
ISS-006 | Rudra Pratap Dubey | 2026-09-04 08:30 | Code Execution | Project code not executing properly in Techyblocks ('project (6).techyguide'). | project (6).techyguide | Diptiban Nayak | Inspected and fixed runtime logic/script conflicts. | Resolved | 2026-09-04 09:15 | Diptiban confirmed fix; Rudra re-tested and confirmed it is working.
ISS-007 | Vibha Prajapati | 2026-09-04 08:50 | Looks / Graphic Effects | Letter sprite is still not changing its color when executing block 'change color effect by ()'. | — | Diptiban Nayak | Identified graphic effects shader/canvas bug for letter sprites; fix scheduled. | In Progress | Fix in Progress | Diptiban confirmed: 'We will fix it shortly for colour changing process.'
ISS-008 | Rudra Pratap Dubey | 2026-09-04 (Teams) | Assets / Game Project | Missing 'Bowl' sprite in asset library for 'Catch the Apple' game project. | Teams Image | Diptiban Nayak | Checking asset repository to introduce bowl/catcher sprite for game activity. | In Progress | Under Review | Reported via Teams Software Testing Group.
DEV-001 | Diptiban Nayak (Task Update) | 2026-09-04 | Sound Engine | Sound section functionality and audio playback support inside Techyblocks app. | Techyblocks Core | Development Team | Worked on and optimized the sound section of the Techyblocks app. | Resolved | 2026-09-04 | Sound engine enhancements integrated into build.
DEV-002 | Diptiban Nayak (Task Update) | 2026-09-04 | Sensing / Input | User input collection block ('ask [ ] and wait') implementation. | Techyblocks Core | Development Team | Implemented 'ask' block to capture and store user input values dynamically inside app. | Resolved | 2026-09-04 | Prompt modal and 'answer' variable binding verified.